## Sheet1
Deadline(*)
In Progress
Completed
Not Completed
|  |  | Semester 1 | [11 empty] | Semester 2 | [11 empty] | Assessment Weeks
Task | Detail | Time (Hrs) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W1 | W2
Choose a supervisor | View available supervisors and email ones of interest | 0.5 | bar: Semester 1 W1 to Semester 1 W2
Confirm supervisor | Confirm supervisor and project idea and organise weekly meetings | 0.5 | bar: Semester 1 W3
RESEARCH AND PLANNING (124 hours) | bar: Semester 1 W1 to Semester 1 W12
Create Terms of Reference (TOR) | The terms of reference is a document that the project will be measured against. | 10 | bar: Semester 1 W4 to Semester 1 W7
Complete Ethics form | Online ethics form to be completed so that the project is inline with the university's standards and has ethical approval | 3 | bar: Semester 1 W5
TOR review meeting | Go through the TOR with supervisor and second marker | 1 | bar: Semester 1 W7
Revise TOR | If any suggestions come up in the TOR meeting, revise the TOR during this period | 2 | bar: Semester 1 W8
Create Literature Review | Create a literature review of all the reports that will be useful within my project so that I can get a better understanding of how I can create my system | 40 | bar: Semester 1 W9 to Semester 1 W11
Establish Client Requirements | Speak to client and note down all the things they require in the system. | 5 | bar: Semester 1 W10
Create initial storyboard and vision of product | Create initial storyboard using wireframes and present the vision of the product to the client | 10 | bar: Semester 1 W11
Persona(s) and Scenarios of target audience | Find target audience of the product and create persona(s) and scenarios | 10 | bar: Semester 1 W10 to Semester 1 W11
User Requirement Document | Compile a user requirements document using all the above material and anything else that may be useful | 10 | bar: Semester 1 W10 to Semester 1 W11
Create draft chapters for the research and planning aspects | Start drafting up the chapters for the report in regards to the researching and planning sections | 30 | bar: Semester 1 W10 to Semester 1 W11
Submit chapters to supervisor for review | Send the chapters to supervisor and get his opinion on what needs to be changed | 1 | bar: Semester 1 W11
Discuss plans for Semester 2 | Discuss in details on what needs to be done in the next semester to have a successful project | 2 | bar: Semester 1 W12
DESIGN AND BUILD (130 hours) |  |  | Semester 2 W1: DESIGN AND BUILD (120 hours)
Create UML diagrams of the system |  | 10 | bar: Semester 2 W1
Create Low Fidelity Prototype |  | 10 | bar: Semester 2 W2
Create Entity Relationship Diagram and Data Dictionary |  | 5 | bar: Semester 2 W2 to Semester 2 W3
Create the database |  | 5 | bar: Semester 2 W4 to Semester 2 W5
Development of the server-side |  | 20 | bar: Semester 2 W5 to Semester 2 W6
Development of the client-side |  | 60 | bar: Semester 2 W6 to Semester 2 W7
Development of the CRM System |  | 20 | bar: Semester 2 W6 to Semester 2 W7
TESTING AND EVALUATION (40 hours) |  |  | Semester 2 W7: TESTING AND EVALUATION
Functional Testing |  | 10
Usability Testing |  | 10
Make changes based on testing processes |  | 10
Evaluate Product |  | 5
Evaluate the processes and own performance |  | 5
WRITING THE REPORT (110 hours) |  |  | Semester 1 W7: WRITING THE REPORT (100 hours)
Abstract |  | 3
Introduction |  | 10
Research and Planning |  | 25 | bar: Semester 1 W9 to Semester 1 W12
Design, Implementation and Testing |  | 25
Evaluation |  | 25
Conclusions and Recommendations |  | 10
Send for feedback |  | 1
Make changes based on feedback |  | 10
Submit report |  | 1 | bar: Semester 2 W12
VIVA (2 hours)
Organise Viva |  | 1
VIVA Presentation |  | 1 | bar: Assessment Weeks W2
| Total Time | 407